## Risk Plan
Project |  |  | Maglev Train
Start |  |  | 2025-11-03
End |  |  | 2026-10-30
Project Manager |  |  | Sakka Mohamad-Mario
PROJECT RISK MANAGEMENT PLAN
|  |  | Identification | [5 empty] | Qualitative Analysis |  |  | Quantitative Analysis |  |  |  | Response Strategy |  | Monitoring and Control
Priority | Status | ID # | Date Identified | Project Phase | Functional Assignment | Threat/Opportunity Event | Risk Trigger | Type | Probability (β) | Impact (i) | Risk Matrix (11) | Probability (λ) | Impact ($ or days) | Effect ($ or days) | Strategy | Response Actions including advantages and disadvantages | Affected WBS Tasks | Responsibility (Task Manager) | Status Interval or Milestone Check | Date, Status and Review Comments
High | Active | 1 | 2025-11-17 | Supplier Qualification / Long-Lead POs | Procurement / Power Electronics | Supply chain delays for inverter stacks and critical sensors | Long lead-times, supplier capacity constraints, QA rejections | Threat | Moderate | High |  | 30% | 30 | 9 | Mitigate | Mitigation: Early supplier engagement; multi-source key parts; long-lead POs Contingency: Re-plan build; approved alternates; buffer stock draw |  | Al-Khalidy Essam | Supplier Qualification / Long-Lead POs | PO slippage > 2 weeks; supplier OTD < 90%
High | Active | 2 | 2026-02-02 | EMC Pre-Compliance / Type Tests | EMC & Safety | EMI/EMC non-compliance requiring redesign or shielding changes | Emissions/immunity test failures; unexpected coupling on guideway coils | Threat | Low | Very High |  | 15% | 60 | 9 | Mitigate | Mitigation: Pre-compliance tests; layout reviews; EMC FMEA Contingency: Add shielding/ferrites; retest window pre-booked |  | Al-Khalidy Essam | EMC Pre-Compliance / Type Tests | Pre-comp failures; high noise on position sensors
High | Active | 3 | 2026-05-15 | HIL / System Integration | Embedded SW & Control | Integration latency or instability breaks headway/stopping accuracy | End-to-end loop > spec; jitter > budget in HIL/integration | Threat | Moderate | High |  | 30% | 30 | 9 | Mitigate | Mitigation: Real-time profiling; rate-monotonic scheduling; HIL early Contingency: Fallback degraded mode; OTA fix plan |  | Zafar Azzam | HIL / System Integration | Cycle time spikes; watchdog resets
High | Active | 4 | 2026-10-01 | Safety Case / Certification Review | Safety / RAMS | Safety case/certification schedule slips before trial service | Additional regulator evidence; late audit findings | Threat | Moderate | Very High |  | 30% | 60 | 18 | Mitigate | Mitigation: Progressive hazard closure; authority reviews; V&V traceability Contingency: Stage trial without passengers; documentation sprints |  | Sakka Mohamad-Mario | Safety Case / Certification Review | Open hazards above threshold; audit nonconformities
Medium | Active | 5 | 2026-03-31 | Grid Study / Power-On | Power Interface | Grid interconnect capacity/quality limits ramp profiles and tests | Utility constraints; harmonic/PF limits tighter than expected | Threat | Low | High |  | 15% | 30 | 4.5 | Mitigate | Mitigation: Early utility studies; active filters; PF correction Contingency: Rent temporary power; reduce test envelope |  | Al-Khalidy Essam | Grid Study / Power-On | Utility study flags limits; THD above spec
Medium | Active | 6 | 2026-01-20 | Guideway Build / Commissioning | Civil / Guideway | Guideway alignment or survey errors affect levitation stability | Survey inaccuracies; thermal expansion unaccounted | Threat | Low | High |  | 15% | 30 | 4.5 | Mitigate | Mitigation: Independent survey; thermal allowances; as-built scans Contingency: Local shimming/grouting; speed restrictions |  | Sakka Mohamad-Mario | Guideway Build / Commissioning | Track geometry out of tolerance; ride quality dips
Medium | Active | 7 | 2026-04-10 | Thermal Validation / Soak Tests | Thermal / Power Electronics | Cooling underperformance in inverter cabinets at summer ambient | Undersized HX; fouled filters; fan curve mismatch | Threat | Moderate | Moderate |  | 30% | 14 | 4.2 | Mitigate | Mitigation: Thermal CFD; margin on exchangers; DP monitoring Contingency: Retrofit larger HX; increase airflow |  | Al-Khalidy Essam | Thermal Validation / Soak Tests | Coolant temps high; inverter derates
Medium | Active | 8 | 2026-05-01 | Release Train / Beta | Software Configuration | Regression due to rapid change cadence across modules | Insufficient integration testing; branch drift | Threat | Moderate | Moderate |  | 30% | 14 | 4.2 | Mitigate | Mitigation: CI with HIL smoke tests; release gates; feature flags Contingency: Rollback to LTS build; hotfix protocol |  | Zafar Azzam | Release Train / Beta | Failed nightly HIL; unit coverage drops
Medium | Active | 9 | 2026-02-15 | Procurement / Manufacturing | Project Controls | Budget overrun from materials price volatility (copper, magnets) | Market spikes; currency movement | Threat | Low | High |  | 15% | 200000 | 30000 | Mitigate | Mitigation: Hedging; vendor price locks; contingency reserve Contingency: Descoping options; draw down management reserve |  | Sakka Mohamad-Mario | Procurement / Manufacturing | Commodity index rising; vendor re-quote
Medium | Active | 10 | 2025-12-10 | Permitting / Public Hearing | Permitting / Stakeholders | Community opposition delays permits or restricts operating window | Noise/EMF concerns; visual impact | Threat | Low | High |  | 15% | 30 | 4.5 | Mitigate | Mitigation: Early outreach; transparent EMF/noise data; mitigation walls Contingency: Adjust operating profile; additional barriers |  | Sakka Mohamad-Mario | Permitting / Public Hearing | Public comments spike; hearing postponements
Medium | Active | 11 | 2026-03-05 | Noise/Vibration Tests | Acoustics / Ride Quality | Vibration or noise exceeds local limits at certain speeds | Resonance on guideway; panel rattling | Threat | Low | High |  | 15% | 30 | 4.5 | Mitigate | Mitigation: Modal testing; tuned damping; fastening audits Contingency: Speed caps in affected zones; damping retrofits |  | Al-Khalidy Essam | Noise/Vibration Tests | FFT peaks near limits; complaints during trials
High | Active | 12 | 2026-01-05 | Supplier Risk Review | Supplier Management | Single-source vendor fails financially or exits market | Bankruptcy; M&A disruption | Threat | Low | Very High |  | 15% | 60 | 9 | Mitigate | Mitigation: Financial health checks; dual-source; escrow for design files Contingency: Emergency re-source; redesign to alternate |  | Sakka Mohamad-Mario | Supplier Risk Review | Credit rating downgrade; late payroll news